## UQ Status
No. | Document Title | Cisco | HP | 3M | OEM Partner | UBQS (HOPE) | Ubiquoss document (by products)
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[7 empty] | C9516 | C9500 | C9504N | C4000 | CS-8002A | C1004 | C1004W | C1004P
1 | Data Sheets | √ | √ | √ | √ | √ | bar: Ubiquoss document (by products) 1 to Ubiquoss document (by products) 8
2 | Installation Guides | √ |  |  | √ | √ | bar: Ubiquoss document (by products) 1 to Ubiquoss document (by products) 8
3 | Brochures | √ | √ | √ |  | √
4 | User Manuals | √ |  |  | √ | △ | △ | O | X | X | X | X | X | X
5 | Case Studies | √ | √ | √ | bar: √ to √ △
6 | Q&A | √ | √ | bar: √ to √ △
7 | Troubleshooting TechNotes | √ |  | √ | bar: √ to √ △
| C9500 User Guide for Charter | 6 |  |  | √ O: 3월 2일 최 우선 순위로 진행 됨
No. | Product | Man-Hours |  | Start | √ △: End; √ O: 비 고
1 | C9516 Data Sheet | 2 |  | 2016-03-02 | √ △: 2016-03-02; √ O: Update 필요
2 | C9516 Installation Guides | 2 |  | 2016-03-02 | √ △: 2016-03-02; √ O: Update 필요
3 | C9500 Data Sheet | 3 |  | 2016-03-03 | √ △: 2016-03-03; √ O: 다량의 Update 필요
4 | C9516 Training support | 10 |  | 2016-03-03 | √ △: 2016-03-07; √ O: Feedback 후 재 검토 필요
5 | C9500 User Manual | 20 |  | 2016-03-04 | √ △: 2016-03-07; √ O: 심각한 Update 필요
6 | C9516 User Manual | 10 |  | 2016-03-07 | √ △: 2016-03-08; √ O: 심각한 Update 필요
|  | 47 |  | 4
No. | Product | Man-Hours |  | Start | √ △: End; √ O: 비 고
7 | C9500 Installation Guides | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: Update 필요
8 | CS-8002A Data Sheet | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: Update 필요
9 | CS-8002A Installation Guides | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: Update 필요
10 | C1004P Installation Guides | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: 감수
11 | C1004 Data Sheet | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: Update 필요
12 | C1004 Installation Guides | 2 |  | 2016-03-09 | √ △: 2016-03-09; √ O: Update 필요
13 | C1004W Data Sheet | 2 |  | 2016-03-10 | √ △: 2016-03-10; √ O: 사진 변경 필요
14 | C1004W Installation Guides | 2 |  | 2016-03-10 | √ △: 2016-03-10; √ O: 사진 변경 필요
15 | C4000 Data Sheet | 8 |  | 2016-03-10 | √ △: 2016-03-10; √ O: 최초 작성
16 | C4000 Installation Guide | 4 |  | 2016-03-11 | √ △: 2016-03-11; √ O: 추가 변경 필요
17 | C9504N Data Sheet | 10 |  | 2016-03-11 | √ △: 2016-03-14; √ O: 최초 작성
19 | C9504N Installation Guides | ? |  |  | √ O: 한글 문서 취합
|  | 38 |  | 4
18 | C4000 User Manual | ? |  |  | √ O: 영문 문서 작성
19 | CS-8002A User Manual | ? |  |  | √ O: 영문 문서 작성
20 | C1004 User Manual | ? |  |  | √ O: 영문 문서 작성
21 | C1004W User Manual | ? |  |  | √ O: 영문 문서 작성
| Brochures support | 5 |  | 2016-03-31 | √ △: 2016-04-05
| Comcast Presentation | ? |  | 2016-03-11 | √ △: 2016-03-24
No. | Document Title | Cisco | HP | 3M | √: OEM Partner; √ △: UBQS (HOPE); √ △: Ubiquoss document (by products)
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[7 empty] | C9516 | C9500 | C9504N | C4000 | CS-8002A | C1004 | C1004W | C1004P
1 | Data Sheets | √ | √ | √ | √ | √ | bar: Ubiquoss document (by products) 1 to Ubiquoss document (by products) 8
2 | Installation Guides | √ |  |  | √ | √ | bar: Ubiquoss document (by products) 1 to Ubiquoss document (by products) 8
3 | Brochures | √ | √ | √ |  | √
4 | User Manuals | √ |  |  | √ | △ | △ | O | X | X | X | X | X | X
5 | Case Studies | √ | √ | √ | bar: √ to √ △
6 | Q&A | √ | √ | bar: √ to √ △
7 | Troubleshooting TechNotes | √ |  | √ | bar: √ to √ △
※ 번호는 우선 순위 임
※ 각 제품의 산출물을 조합하여 교육자료 작성
금주 완료
차주 완료

## Cisco_ref.
Company | Category | Title | Description
Cisco | Technology information | Technologies digests | Description of benefits and functionality of particular networking technologies or protocols, as well as Cisco's relationship to them.
|  | Technology briefs | Details about the role of each technology, including evolution, capabilities, and common usage.
|  | Technology Q&A | Questions and answers related to a specific product or technology.
|  | Technology white paper | Explains an aspect of technology to help you understand it, rather than how to implement it- often with references to actual configurations or installations.
| SW downloads, release and general information | Compatibility information | Lists which Cisco SW versions can be used with a particular Cisco HW product or module.
|  | Release notes | Description of new features, system requirements, limitations, and restrictions, caveats, and troubleshooting information for a particular SW release. * may also include relevant installation instructions
|  | Licensing information | Information about licenses for open-source SW included in a Cisco product. * may also contain information about other types of licenses associated with a product.
|  | Documentation roadmaps | Describe a set of product documents, and how the documents relate to one another, for a specific Cisco product. Documentation roadmaps contain links to the documents that are referenced.
| Reference guides | Command references | Information about the SW commands used to configure Cisco products, including command syntax, default value, value range, command mode, usage guidelines, and examples. * command summary guides contain a subset of this information
|  | Technical references | A wide range of technical information as it pertains to Cisco products and services, including system test reports and MIB reference information.
| Design | Design guides | How to plan, install, and configure a Cisco product. Information about the product's supported technologies, interfaces, and protocols and can also contain special instllation considerations, network diagrams, example applications, system design, and environmental recommendations.
|  | Design technotes | Instructions to help or inform you.
| Install and upgrade | Install and upgrade guides | Step-by-step instrucions for installing or upgrading a cisco product or module.
|  | Install and upgrade technotes | Instructions to help or inform you.
| Configure | Configuration guides | Detailed, step-by-step instructions for configuring a Cisco product or module, including configuration examples, network diagrams, and technical concepts.
|  | Configuration examples and technotes | How to configure a product in a particular network with tips and a sample network diagram
|  | Programming guides | Reference material and the development instructions needed for programmers and system administrators to customize the functionality of their Cisco products and to deploy new services.
| Troubleshoot and alerts | Error and system messages | Error and system messages for a Cisco product, including any recommended user action for each message.
|  | Field notices | Non-urgent, usage related alerts about a specific product or technology.
|  | Password recovery | How to recover passwords on Cisco products.
|  | Security advisories, responses and notices | Procedures you must use if you are experiencing an active security attack or if there is an eminent security risk to a specific platform or system.
|  | Troubleshooting guides | Problem-solving techniques for Cisco products, including methods to identify problems based on symptoms and recommended actions for resolution.
|  | Troubleshooting technotes | Instructions to help or inform you.
| Maintain and operate | End-user guides | Information about installing, configuring, and using a Cisco product. * can include safety regulations and procedural details for the hardware products.
|  | Maintain and operate guides | Describes the tasks required to maintain, administer, and use a Cisco product.
|  | Maintain and operate technotes | Instructions to help or inform you.
<Product documentation for a larger product line>
http://www.cisco.com/c/en/us/support/interfaces-modules/content-switching-module/model.html#~tab-documents
• Solutions to Common Problems
• Command References
• Configuration Examples and TechNotes
• Configuration Guides
• Data Sheets
• Install and Upgrade Guides
• Release Notes
• Applied Mitigation Bulletins
• At-a-Glance
• Brochures
• Bulletins
• Case Studies
• Design Guides
• Design TechNotes
• End-User Guides
• End-of-Life and End-of-Sale Notices
• Error and System Messages
• Field Notices
• Install and Upgrade TechNotes
• Licensing Information
• Maintain and Operate Guides
• Presentations
• Press Coverage
• Q&A
• Security Advisories, Responses and Notices
• Solution Overviews
• Technical References
• Troubleshooting Guides
• Troubleshooting TechNotes
• White Papers

## HP & 3M_ref.
Company | Archive name | Document type | Description
hp | Product Documentation | Business white paper | Describes the business benefits of a vendor's offering to supplement a product launch, argue a business case, or support a technical evaluation at the bottom of the sales funnel
|  | Case study | Product success story about how a company solved a problem using a specific product, process, method or idea. A soft-sell proposition designed to compel prospects to request more detailed information.
|  | Analyst report | Commissioned report or whitepaper to help highlight the company's industry message, often on best practices to solve business pain points (without an outright company endorsement)
|  | Solution brief | to help audience envision how a given product can supply certain capabilities
|  | Data sheet | Document that summarizes the performance and other technical characteristics of a product in sufficient detail to be used by a design engineer to integrate the component into a system
|  | Product family guide | Introduction into the categorisation methods used for products & solutions
|  | Technical white paper | Technical document that describes how a technology or product solves a particular problem
|  | Quick spec | Summarized product spec
|  | Brochure | Informative paper document used for advertising that can be folded into a template, pamphlet or leaflet
|  | Reference guide | In-depth resource about a topic
|  | Faq/Q&A | Information about products in question-and-answer format
3M | document library | Additional picture
|  | Article reprint | Customized article reproductions of material to educate audience and reinforce product message
|  | Brochure | Informative paper document used for advertising that can be folded into a template, pamphlet or leaflet
|  | Bulletin | Updated news and information about products, including alerts for product upgrades and revisions
|  | Case study | Published report about a person, group, or situation that has been studied over time
|  | Competitive information | Gathering of information about competitors and use of that information to gain a business advantage
|  | Data sheet | Document that summarizes the performance and other technical characteristics of a product in sufficient detail to be used by a design engineer to integrate the component into a system
|  | Flyer | Form of paper advertisement intended for wide distribution and typically posted or distributed in a public place or through the mail
|  | Info | Product information
|  | Instruction sheet | For training purposes
|  | Instructions_manual | For operation purposes
Main picture
|  | MSDS/PSDS | Material safety data sheet/product safety data sheet
|  | News release | Written or recorded communication directed at members of the news media for the purpose of announcing something ostensibly newsworthy
|  | Regulatory material | Information about rules, proposed rules and notices
|  | Technical paper | Technical document that describes how a technology or product solves a particular problem